## Sheet1
iteration3 Time Recording Log
Student | ZihaoHuang
Program
Instructor
Project | Phase | Date | Start | Int Time | Stop | Delta Time | Comments
iteration3 | Classes diagram | 2016-10-19 | 10:00 |  | 11:00 | 60mins | update
| Coding | 2016-10-19 | 13:00 |  | 17:00 | 240mins
| Testing | 2016-10-21 | 14:00 |  | 3:30:00 p.m | 120mins
| TestingReport | 2016-10-21 | 15:30 |  | 4:30:00 p.m | 30mins
| Document | 2016-10-22 | 10:00 | 60mins | 5:30:00 p.m | 150mins
| Layout | 2016-10-23 | 14:00 |  | 3:00:00 p.m | 60mins

## Instructions
Time Recording Log Instructions
General | - Record all of the time you spend on the project.
- Record the time in minutes.
- Be as accurate as possible.
- If you need additional space, use another copy of the form.
- If you forget to record the starting, stopping, or interruption time for an activity, promptly enter your best estimate.
Header | - Enter your name and the date.
- Enter the program name and number.
- Enter the instructor’s name and the programming language you are using.
Project | Enter the program name or number.
Phase | Enter the name of the phase for the activity you worked on, e.g. Planning, Design, Test.
Start Date and Time | Enter the date and time when you start working on a process activity.
Interruption Time | - Record any interruption time that was not spent on the process activity.
- If you have several interruptions, enter their total time.
- You may enter the reason for the interrupt in comments.
Stop Date and Time | Enter the date and time when you stop working on that process activity.
Delta Time | Enter the clock time you actually spent working on the process activity, less the interruption time.
Comments | Enter any other pertinent comments that might later remind you of any unusual circumstances regarding this activity.